## Sheet1
Addition/Modification To Schematic Sheet | Status
Fix decoupling caps | 1
Delete battery backup | 1
Figure out the oscillator's capacitors and connection | 1
Double check the PICKit3 programming headers, do I want the extra cap? | 1
Examine the oscillator | 1
Build new Buck converter for 3.3V | 1
Build screen backlight driver | 1
Are any resistors or caps needed on the PMP or PMA linse? | 1
Filter PIC32 AVDD pin | 1
Check NAND connections | 1
IC for rotary encoder might not work, we need to know forward from backward | 1
Verify USB data connection, what is 3v3 and Device ID | 1
Add ferrite to ADC | 1
Reorganize the schematic, add new titles, divide with dotted lines, consider 2-3 sheets | 1
Replace Temp/Humidity Sensor with new one | 1
Relabel RGB nets with "LCD_" first | 1
Size led current limiting resitors (is 100 good?) | 1
Figure out GPS connecctions | 1
Pick new terminal blocks | 1
Verify that charge pump is a good idea | 1
Remove USB ID from power USB port | 1
Redo the passives/diodes on the screen supply | 1
Change the pin lengths of some devices | 0 | x
Split schematic in 2-4 pages | 1
Change the schematic symbol for devices so gnd isn't on the bottom | 0 | x
Add description: USB Peripheral Port | 1
TP symbols | 0
Delete all but 2 LEDs and BTNs | 0 | x
Make anode and cathode power flag, label with 24V | 1
Make unique buffer symbol | 0 | x
Replace JPs on Rotary encoder with 0ohm resistors symbol | 1
Change LEDs layout so eliminate unecessary height | 1
Fix 'J' location on terminal block | 1
Either add value ferrite to ADC or remove it | 1
Double check that the PIC32 ADCs are fine without filtering on the buck converter | 1
Label Decoupling caps with title | 1
Move SRAM to the left | 1
Look for other unique symbols that can be made | 1
Move TFT LCD symbol up | 1
Check that the device address of the Touch Driver, Accel,Temp, and GPS are compatible | 1
Get consistent with how pins are labeled, accel has text labels | 1
Check that all section labels (with bar) are the same size | 1
Check that buffers' OE pins should be tied low | 1
Label unused adc pins as DNP | 1
Consider changing the 2.2kohm resistors on ADC buffer lines to something else | 1
Put a dotted box around the AGND ADC area, consider moving star ground point over | 1
^Noted above, redesign ADC symbol so that it can be divided by dotted box | 1
Check 10k pullup on screen supply, should mabye be 4.7k | 1
Move all identifiers to top and part numbers to bottom | 1
Pick actual parts for resistors, capacitors, diodes (for R and C, look at 3v3 converter DS) | 1
Move pickkit down by USB and terminal block | 1
Change XO | 1
EDS protection on terminal block | 1
Reverse polarity protection on 12 battery | 1
Does the 3v3 converter need a linear stage? | 1
New GPS | 0 | x
New Buffer | 1
New Motor Driver | 0
Add bulk capacitance to motor driver | 1
does power supply need bulk capacitance? | 1
Add fiducials | 0
Fix decoupling caps | 1
Eliminate Unused test points | 1
Move test points to solder pads, not headers | 1
Delete battery backup | 1
Figure out the oscillator's capacitors and connection | 1
Double check the PICKit3 programming headers, do I want the extra cap? | 1
Examine the oscillator | 1
Build new Buck converter for 3.3V | 1
Build screen backlight driver | 1
Are any resistors or caps needed on the PMP or PMA linse? | 1
Filter PIC32 AVDD pin | 1
Check NAND connections | 1
IC for rotary encoder might not work, we need to know forward from backward | 1
Verify USB data connection, what is 3v3 and Device ID | 1
Add ferrite to ADC | 1
Reorganize the schematic, add new titles, divide with dotted lines, consider 2-3 sheets | 1
Replace Temp/Humidity Sensor with new one | 1
Relabel RGB nets with "LCD_" first | 1
Sets of caps for ADC | 1
Replace both buffers with new symbol | 1
Change USB to 5V | 1